## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Brandon | 7000 | 5750 | 1250 | 3700 | 3100 | 600 | 2000 | 1350 | 650 | 1300 | 1300 | 0
Josh | 13000 | 8150 | 4850 | 9800 | 5600 | 4200 | 2000 | 1350 | 650 | 1200 | 1200 | 0
Lucas | 6200 | 4250 | 1950 | 3000 | 2000 | 1000 | 2000 | 1150 | 850 | 1200 | 1100 | 100
Sheldon | 3800 | 2700 | 1100 | 600 | 400 | 200 | 2000 | 1200 | 800 | 1200 | 1100 | 100
Connor | 4700 | 2450 | 2250 | 1500 | 300 | 1200 | 2000 | 950 | 1050 | 1200 | 1200 | 0
Jubal | 3700 | 1150 | 2550 | 500 | 200 | 300 | 2000 | 550 | 1450 | 1200 | 400 | 800
Total | 38400 | 24450 | 13950 | 19100 | 11600 | 7500 | 12000 | 6550 | 5450 | 7300 | 6300 | 1000

## Gantt
| Predicted Time(hrs) | Time Spent(hrs) | key: |  | completed |  |  | this week |  |  | planned
Brandon |  |  | hours: | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78 | 81 | 84 | 87 | 90 | 93 | 96 | 98 | 101 | 104 | 107
gantt chart creation | 3 | 3
track health changes | 6 | 6
track time changes | 3 | 5
user interface setup | 12 | 5
create caravel physics | 2 | 2
level creation | 8 | 6
testing | 3 | 4
totals | 37 | 31
Josh
logo creation | 3 | 2
player character modeling | 5 | 16
model Animation | 5 | 12
object / environment assets model | 30 | 15
object / asset animations | 20 | 5
perk system | 15 | 3
placeholder | 0 | 0
testing | 20 | 3
totals | 98 | 56
Lucas
background music | 5 | 2
UI sounds | 2 | 2
entity effects | 3 | 1
terrain effects | 2 | 1
demo/stress test | 15 | 11
testing | 3 | 3
totals | 30 | 20
Sheldon
menu design | 6 | 10
programming ship controls | 4 | 4
User Customizable Input | 2 | 0
pause menu | 4 | 3
end screen | 3 | 2
level creation | 10 | 6
testing | 6 | 4
totals | 35 | 29
Connor
setup GIT Hub | 1 | 3
collision detection | 10 | 4
create unity project | 20 | 4
barrel physics | 3 | 3
placeholder | 0 | 0
testing | 15 | 3
totals | 49 | 17
Jubal
coding standard creation | 2 | 1
level design (2) | 5 | 1
whale movement | 2 | 2
placeholder | 0 | 0
placeholder | 0 | 0
testing | 5 | 2
totals | 14 | 6
group totals (hrs) | 98 | 55
group totals ($) | 9800 | 5500

## Meetings
| Date | Jan. 24 | Feb. 3 | Feb. 5 | Feb. 9 | Feb. 11 | Mar. 17 | Mar. 25 | DATE | DATE | DATE
| Purpose | First Meeting | RFP / Game Planning | SA Presentation Planning / RFP Preparation | Finalized RFP and Presentation | Initial Demo Prep / Game start | Stress Test Prep | Gantt Chart Demo Prep | Future Meeting | Future Meeting | Future Meeting
| Hours | 1.5 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
Brandon | 13.5 | ü | ü | ü | ü | ü | ü | ü
Josh | 13.5 | ü | ü | ü | ü | ü | ü | ü
Lucas | 11.5 | ü | ü | ü | ü |  | ü | ü
Sheldon | 12 |  | ü | ü | ü | ü | ü | ü
Connor | 9.5 | ü | ü | ü | ü |  | ü
Jubal | 5.5 | ü | ü |  |  |  | ü
Totals | 65.5 | 7.5 | 12 | 10 | 10 | 6 | 12 | 8 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Brandon | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Writing RFP - 1.0, 8.0, 9.0, 10.0 | 3 | 3 | bar: 3 to 6
| Merge Gantt Charts | 1 | 1 | bar: 12 to 13
| Assemble SA Powerpoint | 2 | 4 | bar: 14 to 15
| Subtotal | 13 | 13
Josh | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Writing RFP - 5.0, 6.0 | 3 | 3 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 4 | bar: 12 to 13
| Subtotal | 12 | 12
Lucas | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 3 | bar: 7 to 11
| Writing RFP - 2.0, 4.0, 7.0, 10.0 | 3 | 3 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 4 | bar: 12 to 13
| Subtotal | 12 | 11
Sheldon | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 3 | bar: 7 to 11
| Writing RFP - 2.0, 3.0, 5.0, 10.0 | 3 | 3 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 4 | bar: 12 to 13
| Subtotal | 12 | 11
Connor | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 4 | bar: 7 to 11
| Writing RFP - 2.0 | 3 | 3 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 4 | bar: 12 to 13
| Subtotal | 12 | 12
Jubal | Individual schedule | 2 | 1 | bar: 1 to 2
| Champion | 5 | 3 | bar: 7 to 11
| Writing RFP - TBD | 3 | 0 | bar: 3 to 6
| Assemble SA Powerpoint | 2 | 0 | bar: 12 to 13
| Subtotal | 12 | 4
| Total | 73 | 63
red is dependent on others